## Response record
UFCEP6-0-3 Second Release · Feedback response record
Every point raised at a sprint review, the decision taken on it, the action performed, the evidence that the action happened, and the outcome. Two rows are not implemented; their reason, residual risk and proposed future action are in the 'Not implemented' sheet and are not omitted from this one.
ID | Raised at | Point raised | Decision | Action | Evidence | Outcome | Owner (1st / 2nd) | Outstanding work
P-01 | SR2 | The booking model does not show what happens when the external service is unavailable | Add a pending-booking path with a recorded retry | New backlog item; modelled as T_KeepPending with a recorded attempt counter | T_KeepPending in O1; TC-11 executed | Implemented | max / finn | None
P-02 | SR2 | Acceptance criteria must be measurable, not narrative | Rewrite each criterion with a measurement method; retain the original wording alongside it | 28 revised criteria in four families; original 20 retained in the evaluation | Task 04 §§2–3 | Implemented | peter / henry | None
P-03 | SR2 | The repository has no review rule | Protect the main branch and record contribution evidence | Branch protection; contribution matrix in the agile record | git log; contribution matrix | Implemented | henry / max | None
P-04 | SR2 | Presentation claims must be supported by the case study | Add a source column to the assumptions and re-check the requirement list | Source column added; 44 requirements re-checked against case-study paragraphs | assumption-register.md | Implemented | henry / peter | None
P-05 | SR3 | The SR model must be defensible branch by branch | Complete the SR coverage; model the unsupported urgency branch as a soft goal rather than a rule | SR v1.0: 7 actors, 61 elements, 56 links, 9 boundary dependencies | iStar_SR_Initial_Release.svg; SD/SR consistency table | Implemented | finn / henry | None
P-06 | SR3 | Prove that the criteria are measurable | Add a measurement method to each criterion and a coverage map | Measurement method per criterion; coverage map over 18 cases | Task 04 §§3 | Implemented | peter / finn | None
P-07 | SR3 | Pool names do not match the process names inside them | Rebuild the three fragments as one model family with a single participant register | Four models rebuilt; one naming convention P_ / L_ / T_ / G_ / E_ / F_ / MF_ | validate-models.py: 0 structural findings | Implemented | max / henry | None
P-08 | SR3 | Show evidence that the original defects are gone | Publish a before/after validation and deployment comparison | Appendix B comparison of the Sprint 1/2 files against the delivered models | defect-log.md; validation logs | Implemented | peter / max | None
P-09 | SR3 | The i* work must not be presented as having informed the original design | State the timeline wherever the i* models are used | Timeline stated in Tasks 02 and 03 and on slide 3 of the deck | Task 02 §1; Task 03 §1 | Implemented | finn / henry | None
P-10 | SR3 | Agree the urgency classification rules | Obtain the rule from the module team and model the escalation | Asked; no rule was issued before hand-in, so urgency is modelled as a soft goal | none — no rule issued | Not implemented | henry / finn | Rule still outstanding. Urgent-enquiry path stays discretionary. Second-release Must.
P-11 | SR3 | Add automated RBAC regression tests | Automate the role-access and audit checks | Not scheduled: Sprint 4 capacity was consumed by the deployment defects and both evaluations | none — role access evidenced by a live two-role check and by design inspection | Not implemented | peter / finn | RBAC works but cannot be auto-proved to keep working. Second-release Should.
P-12 | SR4 | Put the operational task identifier in the same traceability row as the strategic node | Combine the strategic and operational columns in one row | Traceability table rebuilt with both columns | Task 03 v2 | Implemented | henry / max | None
P-13 | SR4 | Give a recommendation against each reported failure rather than only reporting it | Add a recommendation per failure | Section 6 rewritten with a recommendation per unmet criterion | Task 04 §6 | Implemented | peter / finn | None
P-14 | SR4 | Unimplemented actions are acceptable if the reason is recorded | Record the reason and the outstanding implication for each | Reason and implication recorded for P-10 and P-11 | Agile record §5; 'Not implemented' sheet | Implemented | henry / all | None

## Not implemented
The two points we did not implement
Recorded here in the same detail as the implemented points. The spec asks for unimplemented feedback to be justified, not omitted, and for the residual risk and proposed future action to be identified.
ID | Point raised | Why it was not implemented | What we did instead | Residual risk | Proposed future action
P-10 | Agree the urgency classification rules | The case study states that the hospital has not agreed a complete set of rules for determining urgency, and the module team confirmed that none would be issued before hand-in. There was therefore no rule to model. | Urgency is modelled as a soft goal, not as a business rule. The urgent-enquiry path remains discretionary and is recorded as such in the alignment evaluation. | Two patients presenting the same way could be triaged differently by different call handlers, and the record would not show that the difference was discretionary. | Obtain the rule set from the hospital, model it as a decision table behind the urgency gateway, and add acceptance criteria per urgency band. Classified as a second-release Must.
P-11 | Add automated RBAC regression tests | Sprint 4 had no capacity left once the deployment defects were triaged and both evaluations were re-scoped. The regression suite was the lowest-priority item in the sprint backlog and was dropped rather than half-built. | Role access is evidenced instead by a live two-role check: a user with no role sees 0 tasks, a medical secretary sees 785, and 0 enforcement failures were recorded on 15 October 2026. Role routing is additionally verified by design inspection against the candidate groups in the models. | A future change to a form binding, a candidate group or the engine configuration could silently reopen a role to the wrong team, and no automated check would catch it. | Build a regression script that logs in as each of the ten demonstration users and asserts the visible task set matches the declared candidate groups. Classified as a second-release Should.

## Read me
UFCEP6-0-3 · Feedback response record
Second release · 22 October 2026 · group max / finn / henry / peter
What this file is
The feedback response record required by Section 3 of the assessment specification: for each point raised, the decision, the action, the evidence and the outcome, plus any outstanding work.
Where the feedback came from
Sprint reviews 2, 3 and 4. SR2 and SR3 were held during Sprints 1–3 and SR4 at the end of Sprint 4. The points are recorded in the team's feedback action log.
Counts
14 points raised. 12 implemented. 2 not implemented (P-10, P-11), recorded with reason, residual risk and proposed future action on the 'Not implemented' sheet.
Traceability
Each evidence cell names a file, a model element or a test case identifier. Where no evidence exists, the cell says so rather than being left blank.
Numbering
The identifiers P-01 to P-14 are local to this record. The portfolio's feedback action record numbers the same points in its own scheme; the substance, not the identifier, is what matches.
Related deliverables
The same record is summarised on slides 4 and 5 of the presentation, and summarised again in the planning evidence pack. The three must agree.