# Agile delivery record: Sprints 3 and 4

## 1. Sprints 3 and 4

|  | Sprint 3 | Sprint 4 |
| --- | --- | --- |
| Dates | 13–19 October 2026 | 20–22 October 2026 |
| Sprint goal | Produce draft strategic BPMN models and draft i* models, with a first requirements trace, so that SR3 has a reviewable increment | Integrate the earlier fragments, correct the defects found in them, validate and deploy the final models, complete both evaluations, and hand in |
| Backlog items | 20 (S3-01 to S3-20) | 24 (S4-01 to S4-24) |
| Capacity | 4 people × 5 days × 4 h = 80 h nominal, 116 h planned | 4 people × 3 days × 4 h = 48 h nominal, 80 h planned |
| Outcome | Draft increment v0.9 presented at SR3 | Final increment v1.0 handed in |

Every backlog item carries a first owner, a second owner, an estimate in story points and hours, its dependencies, its acceptance conditions and a status. Four members: max (BPMN and integration), finn (external workers and i* modelling), henry (agile, documentation and traceability), peter (forms, QA and testing). The full Sprint 3 and Sprint 4 backlogs are retained in the repository backlog workbook; the items that carry the final increment are these:

| Item | Task | Owner (1st / 2nd) | Acceptance condition | Status |
| --- | --- | --- | --- | --- |
| S4-01 | Triage every defect found in the Sprint 1/2 models | peter / max | Each of the 16 defect categories is fixed or explicitly superseded | Done |
| S4-05 | Rebuild the three fragments as one integrated model family | max / henry | S1, S2, S3 share one participant register and naming convention; O1 merges all three at task level | Done |
| S4-08 | Deploy the models and re-validate with the Camunda toolchain | peter / max | 0 moddle warnings, 0 lint reports, 0 structural defects per model; all six definitions deploy | Done |
| S4-12/13 | Complete the i* SD and SR models | finn / henry | SD: 16 actors, 40 typed dependencies. SR: 7 actors, 61 elements, 9 boundary dependencies; SD/SR consistency table co-signed | Done |
| S4-16 | Alignment evaluation with a full traceability table | henry / max | 44 requirements traced to a strategic activity, an i* element and an implementation artefact with an evidenced verdict | Done |
| S4-18/19 | Acceptance criteria review and test execution | peter / finn | All 20 original criteria assessed; 28 revised; 18 cases executed against the deployed model with retained evidence | Done |
| S4-21 | Assemble the portfolio | henry / max | Every required deliverable present, named to convention, and linked to its evidence | Done |

## 2. Sprint review records — SR3 and SR4 are scheduled for 19 and 22 October 2026

### Sprint review 3 — scheduled 19 October 2026

Increment presented (`v0.9`). Draft level 1 and level 2 strategic models; a draft SD model; the first traceability table; the revised acceptance criteria.

Against the sprint goal. The strategic models and the draft SD model were complete; the SR model, the alignment narrative and the acceptance evidence were not.

Decisions. (1) Split the strategic view across three models rather than one, and document the abstraction level explicitly. (2) Retain the original acceptance criteria alongside the revisions so that later improvement cannot hide an earlier failure. (3) Treat the pool-naming inconsistency as a defect to fix by rebuild rather than by patch.

Feedback received and the change it produced.

| Point raised | Response | Backlog change |
| --- | --- | --- |
| The booking model does not show what happens when the external service is unavailable | Add a pending-booking path with notification and a recorded retry | New item; delivered as T_KeepPending |
| Acceptance criteria must be measurable, not narrative | Rewrite each criterion with a measurement method; retain the original wording | S4-18 enlarged |
| Pool names do not match the process names inside them | Rebuild the three fragments as one model family with a single participant register | S4-05 created |
| The i* work must not be presented as having informed the original design | State the timeline wherever the i* models are used | Documentation change; applied in Tasks 02 and 03 |
| Show evidence that the original defects are gone | Publish a before/after validation comparison | Appendix B added |

### Sprint review 4 — scheduled 22 October 2026

Increment presented (`v1.0`). The integrated strategic model family; the merged operational model; 68 Camunda Forms; the expanded i* SD and SR models; the alignment evaluation with 44 traced requirements; the acceptance evaluation with 18 executed cases; the deployment and execution evidence.

Against the sprint goal. Everything in the goal was delivered. The models deploy and execute; eighteen acceptance cases passed with no incident.

Not completed. Five criteria remain unmet and cannot be demonstrated on this build: RBAC enforcement, audit immutability, management reporting (the monthly timer has not elapsed), real external integration, and the downtime procedure. The enquiry and reporting processes deploy but were not driven by the execution run. Both are recorded in Task 04, section 6.

Feedback received and the change it produced. Place the operational task identifier in the same traceability row as the strategic node (applied). Give a recommendation against each reported failure rather than only reporting it (applied). Record unimplemented actions with their reason and consequence (applied: two actions remain unimplemented and are logged below).

## 3. Retrospectives

Sprint 3. Went well: the strategic models were produced quickly once the abstraction level was agreed; the second-owner rule held. Did not go well: the SR model slipped, and the i* assumptions note was written in fragments and contradicted itself once. Improvements carried into Sprint 4: agree the abstraction level in writing before modelling; write the assumptions note in one sitting; start the acceptance review earlier.

Sprint 4. Went well: deploying the models to a real Camunda 8 cluster was the single most valuable verification step of the project — it found three XSD sequence violations and a runtime form-binding defect that the moddle round-trip, the lint engine and the Modeler had all passed. Reporting those four defects honestly and then closing them with a clean 18-case run was more defensible than reporting a test plan that had only ever run against stubs. Did not go well: the sprint was planned at 80 hours against 48 nominal, and the final integration landed in the last two days. On a further release: rehearse integration at mid-sprint rather than at the end; build the test harness before the exception paths are specified; treat documentation as scheduled work.

## 4. Marked standups — SU3 and SU4 are scheduled for 15 and 21 October 2026

SU3 — scheduled 15 October 2026, 09:30

| Member | Completed | Next actions | Blockers and handover |
| --- | --- | --- | --- |
| max | S3-02: S1_Strategic_Landscape.bpmn with 24 nodes and 7 external participants; abstraction note drafted | Finish S3-03 (six-lane referral-to-authorisation model) and start the strategic-to-operational map | None blocking. Needs finn's actor list before finalising external participant naming. henry holds the landscape file and can take over. |
| finn | Draft SD model S3-09: 12 actors and 27 dependencies rendered from the JSON model source; i* tooling decision closed | Start S3-10 (SR decompositions) and draft the soft goals | The renderer does not yet draw the resource-dependency arrowhead correctly, so the SVG export is held. henry is second owner on S3-10. |
| henry | S3-13 requirements list closed at 44 identifiers with source sentences; S3-15 filename convention and DoD added to the README; S3-08 version snapshots; traceability started at 35 of 44 rows | Finish the nine open traceability rows, then draft the alignment narrative | The open rows are the non-functional requirements (RBAC, audit, availability, reporting) and cannot be closed until the model boundary is agreed. max is second owner on the traceability table. |
| peter | S3-14 revised criteria table with original wording retained; S3-16 repeatable lint and audit export | Run the lint audit against the three strategic files and prepare the SR3 acceptance slide | One Camunda 8 error remains: a message boundary event without a subscription correlation key. Proposed as a Sprint 4 item rather than patched mid-sprint. |

SU4 — scheduled 21 October 2026, 09:30

| Member | Completed | Next actions | Blockers and handover |
| --- | --- | --- | --- |
| max | S4-05 integration into the three-model family; S4-06 message-flow register; S4-07 correlation-key fix | Finish the abstraction note and produce the exports | The exports need peter's lint result before they are declared final. henry is second owner on the abstraction note. |
| finn | S4-12 SD v1.0 (16 actors, 40 dependencies); S4-14 soft goals with conflicts recorded; S4-15 assumptions reconciled | Finish the SR coverage and co-sign the SD/SR consistency checklist | Dependency: the alignment evaluation needs the final SD element identifiers. henry is waiting on those. |
| henry | S4-16 traceability complete: 44 identifiers, of which 28 fully supported, 12 partly, 2 not supported and 2 out of scope, each with a strategic activity and an implementation artefact; S4-17 ten prioritised improvements; S4-21 portfolio assembly started | Complete the alignment narrative, then run the hand-in check | Assembly needs the frozen i* PDFs and the final exports. max is second owner on the traceability table; peter holds the acceptance evidence. |
| peter | S4-08 deployment and re-validation; S4-19 execution of the acceptance cases | Complete the criteria quality check and the change log, then the hand-in check | Blocker resolved: deployment found and fixed three XSD sequence violations and the form-binding defect. finn is second owner on the test evidence. |

## 5. Feedback action log

| ID | Point raised | Agreed response | Owner (1st / 2nd) | Status |
| --- | --- | --- | --- | --- |
| FB-01 | SR2: the booking model does not show an unavailable external service | Add the pending-booking path with a recorded retry | max / finn | Implemented (T_KeepPending) |
| FB-02 | SR2: acceptance criteria must be measurable | Rewrite with a measurement method; retain the original wording | peter / henry | Implemented |
| FB-03 | SR2: the repository has no review rule | Protect the main branch and record contribution evidence | henry / max | Implemented |
| FB-04 | SR2: presentation claims must be supported by the case study | Add a source column to the assumptions and re-check the requirement list | henry / peter | Implemented |
| FB-05 | SR3: the SR model must be defensible branch by branch | Complete the SR coverage; model the unsupported urgency branch as a soft goal rather than a rule | finn / henry | Implemented |
| FB-06 | SR3: prove the criteria are measurable | Add a measurement method and a coverage map | peter / finn | Implemented |
| FB-07 | SR3: pool names do not match the process names | Rebuild as one model family with a single participant register | max / henry | Implemented |
| FB-08 | SR3: show evidence that the original defects are gone | Publish a before/after validation and deployment comparison | peter / max | Implemented (Appendix B) |
| FB-09 | SR3: the i* work must not be presented as informing the original design | State the timeline wherever the i* models are used | finn / henry | Implemented |
| FB-10 | SR3: agree the urgency classification rules | Obtain the rule from the module team and model the escalation | henry / finn | Not implemented. The hospital has not agreed a complete set of urgency rules (case study, enquiries paragraph) and the module team confirmed none would be issued before hand-in. Implication: urgency remains discretionary, so the urgent-enquiry path is a soft goal rather than a rule, and an urgency-rules decision is a second-release Must. |
| FB-11 | SR3: add automated RBAC regression tests | Automate the role-access and audit checks | peter / finn | Not implemented. Sprint 4 had no capacity once the deployment defects and both evaluations were re-scoped. Implication: RBAC and audit immutability are evidenced by design inspection only, and a regression suite is a second-release Should. |
| FB-12 | SR4: show the operational task identifier in the traceability row | Combine the strategic and operational columns | henry / max | Implemented |
| FB-13 | SR4: give a recommendation against each reported failure | Add a recommendation per failure | peter / finn | Implemented |
| FB-14 | SR4: unimplemented actions are acceptable if the reason is recorded | Record the reason and the outstanding implication | henry / all | Implemented (see FB-10, FB-11) |

## 6. Definition of Done

A task is Done when all of the following hold:

It meets the acceptance conditions agreed at sprint planning.

A second team member has reviewed it.

It is in the shared repository.

It is linked to its evidence.

Models parse with zero moddle warnings and lint with zero Camunda 8 reports.

Exports are regenerated from the same revision as the model.

The task record shows status, current progress, the next action and any handover.

Applied to the final increment: the four models satisfy conditions 1 to 6, and the two evaluations satisfy 1 to 4 and 7.

## 7. Contribution matrix

| Member | BPMN models | i* models | Requirements, traceability and evaluations | Agile, documentation and repository | Standups and reviews | Total |
| --- | --- | --- | --- | --- | --- | --- |
| max | 45% | 10% | 10% | 10% | 25% | 25% |
| finn | 15% | 60% | 10% | 10% | 10% | 25% |
| henry | 15% | 15% | 45% | 60% | 35% | 25% |
| peter | 25% | 15% | 35% | 20% | 30% | 25% |

Each of the five activity columns shows the share of that activity's work carried out by each member, and each column sums to 100%. The Total column is the split of the group mark, which the group agreed at the start of Sprint 1 to divide equally: 25% each. The two are not the same measure — the activity columns record who carried which work, the Total column records how the group agreed to share the mark — which is why a member can hold a large share of one activity and still take an equal share overall.

The distribution follows the roles agreed at the start of Sprint 1 rather than being assigned after the fact.

henry led the two activities that carry the most weight in the assessment. On requirements, traceability and evaluations he owned the requirements list and user stories (PB-05, PB-06), the requirements traceability matrix (PB-07), the alignment evaluation and its 44-requirement trace (PB-36, PB-37) and the change log and criteria revisions (PB-38 to PB-40), and he wrote the alignment narrative. On agile, documentation and repository he owned the product and sprint backlogs and the definition of done (PB-03, PB-04), the repository, README and filename convention (PB-02), the version snapshots (S3-08, S3-15), the feedback action log (PB-42), the retrospectives (PB-43) and the portfolio assembly and hand-in (PB-44). At the standups and reviews he presented the traceability and evaluation findings at both reviews and prepared the records for all four marked activities, which is the largest share of that column.

max retains the largest single-domain share — 45% of the BPMN work, as integration lead — and finn 60% of the i* models, as their author. peter carries 35% of the evaluation activity through the acceptance testing and the forms, and 30% of the standup and review activity, since he presents the execution evidence at each review.

The equal split was agreed because no member carried the project alone: max held the integration, finn the i* models and the external workers, peter the forms and the testing, henry the requirements, evaluations and documentation. The activity columns above show where each of those contributions landed; the Total column is equal by agreement rather than by arithmetic on those columns.

Evidence is the task ownership recorded in the backlog and the contribution record retained in the repository for tutor moderation.